## Sheet1
Onboard Pending List
SR No. | District | Kit Slot | Station Id | Machine Id | Laptop Serial No. | Laptop Name | Station ID Provided Date | L1 Status | L1 Done Date | L2 Status | L2 Done Date | On-Boarding Status | On-Boarding Date /(Pending days)
1 | Balod | 937_KIT_SLOT | 41171 | INSYDE Corp.E07575FB-E691-4790-CC9F-DD1D464D6DDB |  |  | 19-03-2026 | Yes | 21-08-2025 | Yes | 23-04-2026 | Pending | 89 Days pending after L2 Done
2 | Balodabazar-Bhatapara | 937_KIT_SLOT | 42398 | INSYDE Corp.CC952C70-0353-238B-1E73-98AFA9E72873 |  |  | 19-05-2026 | Yes | 10-08-2025 | Yes | 19-05-2026 | Pending | 63 Days pending after L2 Done
3 | Bijapur | 937_KIT_SLOT | 46130 | INSYDE Corp.17CB4427-095A-A81D-6128-3D6BF73CECB4 |  |  | 21-04-2026 | Yes | 21-04-2026 | Yes | 25-05-2026 | Pending | 57 Days pending after L2 Done
4 | Dhamtari | 300_KIT_SLOT | 49175 | AMI7BA51433-F3FB-F1D8-D622-5E14B70DBF04 | 5CD55021B8 | HP | 17-07-2026 | Yes | 16-06-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
5 | Dhamtari | 300_KIT_SLOT | 49174 | AMI1AD0C0FC-BC25-D451-BD8B-12B32AEFCC9C | 5CD55021BX | HP | 17-07-2026 | Yes | 16-06-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
6 | Dhamtari | 300_KIT_SLOT | 49173 | AMI81EEE1CC-62CD-53A0-DAFB-41187EADB48F | 5CD55063NP | HP | 17-07-2026 | Yes | 16-06-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
7 | Dhamtari | 300_KIT_SLOT | 49172 | AMI0DDA5A42-9D92-CAD1-A427-AE60989A9A74 | 5CD55045GZ | HP | 17-07-2026 | Yes | 16-06-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
8 | Dhamtari | 300_KIT_SLOT | 49169 | AMIC36FAF63-72F7-4230-CCD2-7A3EF4F612C5 | 5CD550218L | HP | 17-07-2026 | Yes | 16-06-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
9 | Dhamtari | 300_KIT_SLOT | 49170 | AMI8417C076-A9EF-2481-5A39-9EB2EB0D7DEC | 5CD5502183 | HP | 17-07-2026 | Yes | 16-06-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
10 | Dhamtari | 300_KIT_SLOT | 49171 | AMIA74D8735-0904-F231-C1D8-49FB66257EE1 | 5CD5502198 | HP | 17-07-2026 | Yes | 16-06-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
11 | Gariyaband | 300_KIT_SLOT | 51145 | AMIB70093B4-3565-2242-1B21-E6AA1FE56F22 | 5CD550454G | HP | 17-07-2026 | Yes | 02-07-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
12 | Gariyaband | 300_KIT_SLOT | 51144 | AMI680AF02C-CAF9-FEE7-62AD-C0CD8CCCC306 | 5CD55045JC | HP | 17-07-2026 | Yes | 02-07-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
13 | Gariyaband | 300_KIT_SLOT | 51143 | AMIC84348D9-41C5-CAD0-0350-46C6E6F34C5C | 5CD5504662 | HP | 17-07-2026 | Yes | 02-07-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
14 | Gariyaband | 300_KIT_SLOT | 51147 | AMI04B14DDC-E969-BB84-DE9A-5B1CC5EC35DA | 5CD5506483 | HP | 17-07-2026 | Yes | 02-07-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
15 | Gariyaband | 300_KIT_SLOT | 51146 | AMI72724796-3FB3-C8C4-5352-C6393B817E3A | 5CD550214Y | HP | 17-07-2026 | Yes | 02-07-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
16 | Janjgir-Champa | 937_KIT_SLOT | 52384 | INSYDE Corp.77DABFCD-8C0B-C58A-9539-A5ACE183B5BD | UN31ZSI03X526650660700 | ACER | 19-03-2026 | Yes | 20-08-2025 | Yes | 21-04-2026 | Pending | 91 Days pending after L2 Done
17 | Janjgir-Champa | 937_KIT_SLOT | 52380 | INSYDE Corp.5CB4FBF5-6207- 389E-55E2-8EF4ACF1AA29 | UN31ZS103X52604E450700 | ACER | 19-03-2026 | Yes | 20-06-2025 | Yes | 21-04-2026 | Pending | 91 Days pending after L2 Done
18 | Kondagaon | 300_KIT_SLOT | 56109 | AMIA5675DD9-A683-8FBC-D17B-D4D93CA1BD7B | 5CD55020R4 | HP | 17-07-2026 | Yes | 19-06-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
19 | Kondagaon | 300_KIT_SLOT | 56110 | AMI2EAFA54B-ED12-FF96-C10A-F303EF2C642A | 5CD55063LW | HP | 17-07-2026 | Yes | 19-05-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
20 | Kondagaon | 300_KIT_SLOT | 56111 | AMIF2400A09-6F98-F1EF-72B2-DE5C02ECEB84 | 5CD550219P | HP | 17-07-2026 | Yes | 19-05-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
21 | Kondagaon | 300_KIT_SLOT | 56112 | AMID8ED5633-D2A3-7A19-EFAF-EFCEF9359363 | 5CD55045FH | HP | 17-07-2026 | Yes | 19-06-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
22 | Kondagaon | 300_KIT_SLOT | 56108 | AMI946DC335-D59B-7D19-3CFA-0BA9DD1E8F77 | 5CD55063NF | HP | 17-07-2026 | Yes | 15-06-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
23 | Kondagaon | 300_KIT_SLOT | 56113 | AMIE70A37CC-514C-AF5A-18D1-8E167BFCF6ED | 5CD550219B | HP | 17-07-2026 | Yes | 19-06-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
24 | Kondagaon | 300_KIT_SLOT | 56114 | AMI57D0401C-1219-AB5C-D60B-34B4625C308F | 5CD55045KL | HP | 17-07-2026 | Yes | 19-06-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
25 | Kondagaon | 937_KIT_SLOT | 56097 | INSYDE Corp.561D6675-DF04-6A8A-F1D3-76E285402EAC | UN31ZSI03X52604F650700 | ACER | 19-03-2026 | Yes | 08-08-2025 | Yes | 07-04-2026 | Pending | 105 Days pending after L2 Done
26 | Korba | 937_KIT_SLOT | 57358 | INSYDE Corp.4B8E5D17-A0A5-6353-62D0-4B2CA7EA2390 |  |  | 27-04-2026 | Yes | 28-04-2026 | Yes | 13-07-2026 | Pending | 8 Days pending after L2 Done
27 | Mahasamund | 937_KIT_SLOT | 59120 | INSYDE Corp.ED971B6C-FA87-F025-2240-1A5AED5838A1 |  |  | 19-03-2026 | Yes | 10-09-2025 | Yes | 12-05-2026 | Pending | 70 Days pending after L2 Done
28 | Manendragarh-Chirmiri-Bharatpur(M C B) | 937_KIT_SLOT | 72006 | INSYDE Corp. 64B8AD79-F223-5BE7-4D66-8534BB08F05B |  |  | 19-03-2026 | Yes | 30-09-2025 | Yes | 22-04-2026 | Pending | 90 Days pending after L2 Done
29 | Manendragarh-Chirmiri-Bharatpur(M C B) | 937_KIT_SLOT | 72018 | INSYDE Corp.1473F76B-AA59-FEB5-9406-3FC8CE6C1224 | ZNN01SI07K52402BB0X10 | ACER | 19-03-2026 | Yes | 11-05-2026 | Yes | 13-07-2026 | Pending | 8 Days pending after L2 Done
30 | Raigarh | 300_KIT_SLOT | 62289 | AMIA26EB937-114B-66E4-0C53-662831A1BF6A | 5CD55045B1 | HP | 17-07-2026 | Yes | 24-06-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
31 | Raigarh | 300_KIT_SLOT | 62297 | AMIA2556BC0-C6D1-B91C-7339-7DB676E4E291 | 5CD550218H | HP | 17-07-2026 | Yes | 19-06-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
32 | Raigarh | 300_KIT_SLOT | 62296 | AMIE1363F48-4F5E-2D7B-47E9-06659CCC10F1 | 5CD550210S | HP | 17-07-2026 | Yes | 19-06-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
33 | Raigarh | 300_KIT_SLOT | 62295 | AMIFF365FC4-8664-01E7-75D2-AA909AB809D2 | 5CD550218N | HP | 17-07-2026 | Yes | 19-06-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
34 | Raigarh | 300_KIT_SLOT | 62294 | AMI37FBF9FD-4037-845D-9E5E-63F9A1871882 | 5CD550CSX9 | HP | 17-07-2026 | Yes | 22-06-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
35 | Raigarh | 300_KIT_SLOT | 62293 | AMI7CF53E71-367E-885C-8977-132116567907 | 5CD55021CQ | HP | 17-07-2026 | Yes | 19-06-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
36 | Raigarh | 300_KIT_SLOT | 62291 | AMI5195B770-2033-0197-7E04-41A98EFD07FF | 5CD550218C | HP | 17-07-2026 | Yes | 24-06-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
37 | Raigarh | 300_KIT_SLOT | 62290 | AMI9E2E6E2B-AAC8-8701-C4E4-DC9AD1F7F892 | 5CD55063PQ | HP | 17-07-2026 | Yes | 24-06-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
38 | Raigarh | 300_KIT_SLOT | 62292 | AMI98B863A2-7EFB-F793-8966-FE589EDFA27B | 5CD55021DM | HP | 17-07-2026 | Yes | 24-06-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
39 | Raigarh | 300_KIT_SLOT | 62288 | AMIAFED2DEB-C232-6BAC-5849-7FBF19770E41 | 5CD550452H | HP | 17-07-2026 | Yes | 24-06-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
40 | Raigarh | 300_KIT_SLOT | 62287 | AMI6B84189C-6002-164D-991B-0548BB87A0A9 | 5CD55045K7 | HP | 17-07-2026 | Yes | 19-06-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
41 | Raigarh | 300_KIT_SLOT | 62286 | AMI4A784A12-73AB-7463-9D8C-CD754C5F636B | 5CD550214M | HP | 17-07-2026 | Yes | 19-06-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
42 | Raigarh | 300_KIT_SLOT | 62285 | AMIE8291FCC-2C50-6F54-2525-58E72B52FA8F | 5CD550217X | HP | 17-07-2026 | Yes | 22-06-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
43 | Raigarh | 937_KIT_SLOT | 62284 | INSYDE Corp.04ACE007-E217-150B-93DB-84EDC8DA5915 | UN31ZSI03X526050680700 | ACER | 05-05-2026 | Yes | 29-08-2025 | Yes | 14-07-2026 | Pending | 7 Days pending after L2 Done
44 | Raipur | 300_KIT_SLOT | 63352 | AMIEDFD06ED-C378-AD3B-3C4F-FBFA2D8A3E24 | 5CD55063M6 | HP | 17-07-2026 | Yes | 08-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
45 | Raipur | 300_KIT_SLOT | 63344 | AMI1E3EFFBC-9230-39BF-40FF-C6CC72F1B752 | 5CD550467C | HP | 17-07-2026 | Yes | 08-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
46 | Raipur | 300_KIT_SLOT | 63351 | AMIFDEE1EA9-D9BC-7119-3D4E-4AB2F06EA446 | 5CD5502132 | HP | 17-07-2026 | Yes | 07-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
47 | Raipur | 300_KIT_SLOT | 63350 | AMI1D0A016B-C3F6-026F-2B6A-353D61D7F720 | 5CD55063M2 | HP | 17-07-2026 | Yes | 08-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
48 | Raipur | 300_KIT_SLOT | 63349 | AMI1AC220D2-8513-D246-CDDD-F2BEC81B7689 | 5CD550216Z | HP | 17-07-2026 | Yes | 07-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
49 | Raipur | 300_KIT_SLOT | 63348 | AMI35B08A87-4466-C521-7AC6-C3EB6938919C | 5CD550217F | HP | 17-07-2026 | Yes | 08-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
50 | Raipur | 300_KIT_SLOT | 63347 | AMI0FB2F49B-36EA-4EB0-BE44-80453A137A51 | 5CD55045DS | HP | 17-07-2026 | Yes | 07-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
51 | Raipur | 300_KIT_SLOT | 63346 | AMID758114E-D095-4903-3977-C9050F8BD91D | 5CD550217Q | HP | 17-07-2026 | Yes | 07-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
52 | Raipur | 300_KIT_SLOT | 63345 | AMIABB487F5-25C9-5C50-B7DB-7CEEC3C891BE | 5CD550456R | HP | 17-07-2026 | Yes | 07-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
53 | Raipur | 300_KIT_SLOT | 63353 | AMIAEFB2026-8964-846D-D242-C75D8A6D2735 | 5CD5504590 | HP | 17-07-2026 | Yes | 07-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
54 | Raipur | 300_KIT_SLOT | 63354 | AMI8A329336-73B4-4584-0585-CD43B0B8AD98 | 5CD5502186 | HP | 17-07-2026 | Yes | 08-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
55 | Raipur | 300_KIT_SLOT | 63355 | AMICFEB369A-5808-8325-E67A-B3CC79266D63 | 5CD550459H | HP | 17-07-2026 | Yes | 07-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
56 | Raipur | 300_KIT_SLOT | 63356 | AMIBA9A24C4-F63A-4023-FA61-7117207931E0 | 5CD55063MS | HP | 17-07-2026 | Yes | 07-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
57 | Raipur | 300_KIT_SLOT | 63357 | AMI7F5898C4-B79D-76A8-C12A-67BE1301C977 | 5CD550217D | HP | 17-07-2026 | Yes | 08-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
58 | Raipur | 300_KIT_SLOT | 63358 | AMI9709A953-D15F-6FBB-B9DA-1FA38AF6DD6E | 5CD5502187 | HP | 17-07-2026 | Yes | 07-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
59 | Raipur | 300_KIT_SLOT | 63359 | AMI3CAB976E-542B-91EE-340A-BBEBB8170E6B | 5CD55045NJ | HP | 17-07-2026 | Yes | 07-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
60 | Raipur | 300_KIT_SLOT | 63360 | AMIE8113FFF-A327-8755-C969-933C7B8F2E47 | 5CD550459G | HP | 17-07-2026 | Yes | 07-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
61 | Raipur | 300_KIT_SLOT | 63361 | AMI6CC60A28-A190-2338-1ADA-2E945A7B7F91 | 5CD55020RS | HP | 17-07-2026 | Yes | 03-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
62 | Raipur | 300_KIT_SLOT | 63327 | AMI1859B6C6-DD8D-C53F-F840-7D3BA5D2054C | 5CSD55021CM | HP | 17-07-2026 | Yes | 03-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
63 | Raipur | 300_KIT_SLOT | 63342 | AMI03BE8153-508F-0126-2B1D-4F6A4545A153 | 5CD55021CB | HP | 17-07-2026 | Yes | 03-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
64 | Raipur | 300_KIT_SLOT | 63321 | AMI1E305303-F91E-753C-EFA6-CBECC1F2150E | 5CSD55020YR | HP | 17-07-2026 | Yes | 02-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
65 | Raipur | 300_KIT_SLOT | 63322 | AMI0985C298-94AF-AC12-C51F-323973334E9C | 5CSD55045GS | HP | 17-07-2026 | Yes | 02-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
66 | Raipur | 300_KIT_SLOT | 63323 | AMI376D8B6F-2406-E9BC-D1F3-A8833FFFC84D | 5CSD550219V | HP | 17-07-2026 | Yes | 02-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
67 | Raipur | 300_KIT_SLOT | 63324 | AMI476543D8-6D7C-4C51-E9AF-709229C3BCE8 | 5CSD55045F6 | HP | 17-07-2026 | Yes | 02-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
68 | Raipur | 300_KIT_SLOT | 63325 | AMI72381016-CACA-97A9-3B1D-6549C3A7E2FD | 5CSD55063L4 | HP | 17-07-2026 | Yes | 02-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
69 | Raipur | 300_KIT_SLOT | 63326 | AMI99025412-251E-CA12-FFFE-37D78579B823 | 5CSD550459J | HP | 17-07-2026 | Yes | 03-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
70 | Raipur | 300_KIT_SLOT | 63328 | AMIE0F83954-6747-D5DD-BDE8-F25D166A3F20 | 5CSD550461D | HP | 17-07-2026 | Yes | 02-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
71 | Raipur | 300_KIT_SLOT | 63329 | AMI8BF22C08-0C97-90F1-2904-AFA8A64EEB09 | 5CSD55063PN | HP | 17-07-2026 | Yes | 03-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
72 | Raipur | 300_KIT_SLOT | 63330 | AMI1F4F5FAC-26DA-0CAC-70BD-E8839DE59DE4 | 5CSD55020S0 | HP | 17-07-2026 | Yes | 03-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
73 | Raipur | 300_KIT_SLOT | 63331 | AMI135ECAFA-9D9B-5F1E-C5C3-4CE990D7A546 | 5CSD55021CG | HP | 17-07-2026 | Yes | 06-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
74 | Raipur | 300_KIT_SLOT | 63333 | AMIAF7FF3CD-ED8E-20B5-5887-A7BA6393EEF8 | 5CSD550214J | HP | 17-07-2026 | Yes | 02-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
75 | Raipur | 300_KIT_SLOT | 63343 | AMI231E1324-EB13-E0F3-D780-A447B914A839 | 5CD55044YQ | HP | 17-07-2026 | Yes | 07-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
76 | Raipur | 300_KIT_SLOT | 63340 | AMIA39B40AF-EDB6-A729-14DE-1E9AB5BB0FEF | 5CSD55045B7 | HP | 17-07-2026 | Yes | 02-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
77 | Raipur | 300_KIT_SLOT | 63339 | AMIA3BCF6D4-99DA-5FCD-2823-F5DFAD9BC170 | 5CSD55063K3 | HP | 17-07-2026 | Yes | 03-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
78 | Raipur | 300_KIT_SLOT | 63338 | AMIAE7CCF58-3A69-274D-2FAA-572DB9953AC4 | 5CSD55063JB | HP | 17-07-2026 | Yes | 02-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
79 | Raipur | 300_KIT_SLOT | 63337 | AMI8FD4AEF6-06F0-49C2-44C7-AC0480FD8DD4 | 5CSD55063NK | HP | 17-07-2026 | Yes | 06-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
80 | Raipur | 300_KIT_SLOT | 63336 | AMIB5898FD9-24C7-D7E7-C4A7-9B89310F2CA8 | 5CSD55020ZW | HP | 17-07-2026 | Yes | 03-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
81 | Raipur | 300_KIT_SLOT | 63335 | AMIF0BC2E97-CC5B-A398-2494-7E894741F551 | 5CSD550217N | HP | 17-07-2026 | Yes | 02-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
82 | Raipur | 300_KIT_SLOT | 63334 | AMIFBE031FD-9E17-ED36-C7A1-1034F0883752 | 5CSD550217L | HP | 17-07-2026 | Yes | 02-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
83 | Raipur | 300_KIT_SLOT | 63332 | AMIAA40A4C2-9FCF-D24B-B3F0-2BBDA89E6DF9 | 5CSD55063ND | HP | 17-07-2026 | Yes | 02-07-2026 | Yes | 21-07-2026 | Pending | 0 Days pending after L2 Done
84 | Sarangarh-Bilaigarh | 937_KIT_SLOT | 71021 | INSYDE Corp.4B1CE21C-5480-689D-B0C8-D0639CC23666 | UN31ZSI03X52604EE40700 | ACER | 19-03-2026 | Yes | 22-08-2025 | Yes | 02-05-2026 | Pending | 80 Days pending after L2 Done
85 | Sarangarh-Bilaigarh | 300_KIT_SLOT | 71039 | AMI8593A688-5B54-5FAB-2E17-86BEBD1EFB7B | 5CD55045J9 | HP | 17-07-2026 | Yes | 16-06-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
86 | Sarangarh-Bilaigarh | 300_KIT_SLOT | 71040 | AMI1F6C49B9-A391-9F94-B149-BBD942191E32 | 5CD55020T1 | HP | 17-07-2026 | Yes | 16-06-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
87 | Sarangarh-Bilaigarh | 300_KIT_SLOT | 71041 | AMI75747CE9-D2D9-E2F8-033F-B8D7D60F9FED | 5CD550210J | HP | 17-07-2026 | Yes | 16-06-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
88 | Sarangarh-Bilaigarh | 300_KIT_SLOT | 71042 | AMIBC86CD33-8F4C-6BC5-4A22-78FE9320C152 | 5CD550218T | HP | 17-07-2026 | Yes | 16-06-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
89 | Sarangarh-Bilaigarh | 300_KIT_SLOT | 71043 | AMICFD5A9F8-8132-7156-926D-AAB5AF284031 | 5CD55022CN | HP | 17-07-2026 | Yes | 16-06-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
90 | Sarangarh-Bilaigarh | 300_KIT_SLOT | 71044 | AMI5B4E2316-B3AD-B81E-613B-C3E85F3086BF | 5CD55021DF | HP | 17-07-2026 | Yes | 16-06-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
91 | Sarangarh-Bilaigarh | 300_KIT_SLOT | 71045 | AMI508822C2-D61D-A765-95B3-769EB9DDC2B0 | 5CD55063MX | HP | 17-07-2026 | Yes | 16-06-2026 | Yes | 20-07-2026 | Pending | 1 Days pending after L2 Done
92 | Surajpur | 937_KIT_SLOT | 67169 | INSYDE Corp.A5713B4C-3685-FE9D-256D-AEE395D28334 |  |  | 19-03-2026 | Yes | 13-08-2025 | Yes | 17-07-2026 | Pending | 4 Days pending after L2 Done